## additional term
Additional Term:
min obligation |  | min subject to capacity
phase # | gram/week | gram/week | duration, weeks | asp $/g | sales, $ | tot grams | start step | comments
1 | ***** | ***** | 21 | ***** | ***** | ***** | March 2005 | R&D phase
2 | ***** | ***** | 17 | ***** | ***** | ***** | Aug. 2005
3 | ***** | ***** | 17 | ***** | ***** | ***** | Dec. 2005
4 | ***** | ***** | 13 | ***** | ***** | ***** | April 2006
5 | ***** | ***** | 52 | ***** | ***** | ***** | July 2006
6 | ***** | ***** | 52 | ***** | ***** | ***** | July 2007
| total steps 1 through 6 |  | 171 | ***** | ***** | *****
7 | ***** | ***** | 208 | ***** | ***** | ***** | July 2008 | option of C&C

## phase 7
Phase 7:
Phase # | Planned Phase start | Planned duration (weeks) | Quality limit for 100% invoicing | price $/g | sales, $ | Usable Material, grams | comments
1 | 14.2.2005 |  | N/A | ***** | 100000 | ***** | completed
2 | 1.1.2006 |  | ***** | ***** | 103000 | ***** | completed
3.a | 9.4.2007 |  | ***** | ***** | 138208 | ***** | completed
3.b | 1.3.2008 |  | ***** | ***** | 45936 | ***** | On-going
4 | 1.4.2008 | 15 | ***** | ***** | 300300 | *****
5.a | 14.7.2008 | 24 | ***** | ***** | 762300 | *****
5.b | 1.1.2009 | 52 | ***** | ***** | 1501500 | *****
5.c | 1.1.2010 | 10 | ***** | ***** | 399000 | *****
6 | 15.3.2010 | 80 | ***** | ***** | 4562000 | *****
Total |  |  |  |  | 7913144 | *****
7 | 26.9.2011 | 208 | ***** | ***** | 12500000 | ***** | C&C option